## Sheet1
ARS 9-593(F) SWF Shot Clock
Preliminary Site Review Meeting(s) |  | Not on clock | This is part of the City's approval process - this is where preliminary site acceptance occurs
Full SWF Review |  | 75 calendar days | Application automatically approved if allowable review days not met
Preliminary Application Review |  | 20 calendar days total, Fees are due upon submission | SLA and All Fees submitted with application
| Application w/Plans Submitted | Clock starts the next calendar day after APPLICATION received | Application and Plan reviewed for completeness
Clock stops if application incomplete on day applicant notified
Clock starts again on the next working day after ADDITIONAL INFO received
Move to Plan and Permit Review when Application accepted as complete
Plan and Permit Review |  | Clock continues to run | Plans distributed to all reviewers for concurrent reviewing
|  | Clock stops at issuance of approval/denial on day applicant notified - IF DENIAL, 30 DAY APPLICANT RESUBMISSION CLOCK STARTS NEXT DAY | Applicant has 30 calendar days to resubmit (ARS 9-593(F)(5), start over if time not met
|  | REVISION REVIEW clock starts next working day REVISED APPLICATION SUBMITTED | The City wants to advise that this is noted as a separate clock to ensure proper tracking by all.
|  | Permits review on resubmission now has 30 calendar days to approve. | Full 30 days regardless of the length of the original review. (ARS 9-593(F)(6))
|  | SLA signed by TDOT Director (or designee) | After all reviews are approved
|  | Permit application approved, permit issued, Applicant notified | eMail copy of permit to applicant
Glossary:
SLA - Site License Agreement
SWF - Small Wireless Facility